## Sheet1
Risk Register
A case study of "SANWO", a fictional Fintech company
Prepared by: Zainab Taofeek
Risk ID | Risk Category | Risk Name | Risk Description | Impact Level | Likelihood | Priority | Status | Mitigation Notes | Owner | Date Updated | Next Review Date
R-01 | Cybersecurity | Phishing attacks targeting employees | Fraudulent emails or messages designed to trick employees into revealing sensitive information or login credentials | High | High | High | In progress | Conduct regular security awareness training and implement email filtering solutions | IT Security Team | May 3rd, 2026 | May 13th, 2026
R-02 | Identity & Access Management | Multi-factor authentication not enforced | Lack of additional authentication layers increases the risk of unauthorized access to accounts and systems | High | High | High | Open | Enable multi-factor authentication for all user and administrative accounts | IT Security Team | April 30th, 2026 | May 12th, 2026
R-03 | Insider Threat | Insider threat from staff misuse | Employees may intentionally or unintentionally misuse access privileges, leading to data exposure or system compromise | High | Medium | High | Monitoring | Apply least privilege access controls and monitor employee activities regularly | Human Resources & IT Security | May 4th, 2026 | May 18th, 2026
R-04 | Data Protection | Unauthorized access to customer data | Sensitive customer information may be accessed by unauthorized individuals due to weak access controls | High | Medium | High | In progress | Implement strong access controls, encryption, and regular access reviews | Data Protection Officer | May 3rd, 2026 | May 16th, 2026
R-05 | Application Security | Mobile app security flaws | Vulnerabilities in the mobile application may expose customer data or allow attackers to exploit the platform | High | Medium | High | Open | Perform regular security testing and secure code reviews for the mobile application. | Application Development Team | May 10th, 2026 | May 23rd, 2026
R-06 | Endpoint Security | Malware Infection | Malicious software may infect company devices or systems, causing disruption, data loss, or unauthorized access | Medium | High | High | Monitoring | Install endpoint protection software and keep systems updated with security patches | IT Operations Team | May 4th, 2026 | May 16th, 2026
R-07 | Access Control | Weak Passwords | Employees or users using weak passwords increase the likelihood of account compromise and unauthorized access | High | High | High | In progress | Enforce strong password policies and require periodic password changes | IT Security Team | May 10th, 2026 | May 23rd, 2026
R-08 | Business Continuity | Poor backup processor | Inadequate backup procedures may result in permanent data loss during system failures or cyber incidents | High | Medium | High | Open | Implement automated backups and regularly test data recovery procedures. | Database Administrator | May 3rd, 2026 | May 15th, 2026
R-09 | Human Risk | Lack of Security awareness | Employees may unknowingly expose the organization to cyber threats due to insufficient cybersecurity training | Medium | High | Medium | In progress | Provide ongoing cybersecurity awareness and training programs for employees. | Human Resources & IT Security | May 5th, 2026 | May 17th, 2026
R-10 | Incident Management | Inadequate incident response plan | Failure to establish a proper incident response process may delay detection, containment, and recovery from security incidents | High | Medium | High | Open | Develop and regularly test an incident response plan for security events. | Incident Response Team | May 5th, 2026 | May 17th, 2026
R-11 | Operational | System downtime | Unexpected outages or service interruptions may affect business operations and customer access to services. | High | Medium | High | Monitoring | Implement system monitoring, redundancy, and disaster recovery measures | IT Operations Team | May 5th, 2026 | May 18th, 2026
R-12 | Fraud | Fake Customer Identity | Fraudsters may create fake accounts or use stolen identities to exploit installment payment services | Medium | Medium | Medium | Monitoring | Strengthen identity verification and fraud detection processes during registration | Fraud & Compliance Team | May 4th, 2026 | May 16th, 2026
R-13 | Reputational | Loss of trust | Security incidents or poor service delivery may damage customer confidence and harm the company’s reputation | High | Medium | High | Monitoring | Improve incident communication, customer support, and data protection practices | Customer Experience Team | May 4th, 2026 | May 16th, 2026
R-14 | Third party availability | Cloud Service outage | Disruption of cloud service providers may affect application availability and business operations | High | Medium | High | Monitoring | Use reliable cloud providers and maintain backup recovery strategies for critical services | Cloud Infrastructure Team | May 7th, 2026 | May 21st, 2026
R-15 | Governance | Undocumented security policy | Lack of formally documented security policies may lead to inconsistent security practices and compliance gaps | Medium | Medium | Medium | Open | Develop and maintain formally approved security policies and procedures | Compliance Officer | May 11th, 2026 | May 24th, 2026
R-16 | Compliance | Non - Compliance with laws | Failure to comply with regulatory or data protection requirements may result in legal penalties and reputational damage | High | Medium | High | In progress | Conduct regular compliance reviews and align practices with regulatory requirements | Compliance Officer | May 9th, 2026 | May 22nd, 2026